## Summary
PROJECT DOCUMENT SUMMARY
Al Noor Residential Tower · status date 15-Oct-26 · all figures are live formulas from the register
Total documents | 22
Approved (A + B) | 11
Awaiting response | 7
Overdue | 6
Approval rate | 78.57%
Documents by Status |  | Documents by Discipline
Status | Count | Discipline | Total | Approved | Under Review | Rejected
Draft | 1 | Architectural | 5 | 1 | 2 | 2
Submitted | 3 | Structural | 5 | 5 | 0 | 0
Under Review | 4 | MEP | 5 | 3 | 2 | 0
Approved | 9 | Civil | 3 | 0 | 1 | 1
Approved with Comments | 2 | HSE | 2 | 1 | 1 | 0
Rejected | 3 | QA/QC | 2 | 1 | 1 | 0
Superseded | 0 | Total | 22 | 11 | 7 | 3
Total | 22 | Under Review column includes Submitted.

## Document Register
AL NOOR RESIDENTIAL TOWER — DOCUMENT REGISTER
Project No. ANR-2026 · Client: Al Noor Developments (fictional sample data) · Status and review codes use dropdown lists
Doc No. | Title | Discipline | Type | Rev | Status | Submitted | Due | Returned | Review Code | Days Open | Transmittal
ANR-AR-DWG-001 | Ground Floor Plan | Architectural | Drawing | 0 | Submitted | 2026-10-02 | 2026-10-16 |  | - | 13 | TR-009
ANR-AR-DWG-002 | Typical Floor Plan L2-L12 | Architectural | Drawing | 0 | Rejected | 2026-09-13 | 2026-09-27 | 2026-09-22 | D - Rejected | 9 | TR-007
ANR-AR-DWG-003 | North Elevation | Architectural | Drawing | 2 | Approved | 2026-08-26 | 2026-09-09 | 2026-09-01 | A - Approved | 6 | TR-004
ANR-AR-DWG-004 | Wall Sections | Architectural | Drawing | 0 | Under Review | 2026-08-05 | 2026-08-19 |  | - | 71 | TR-001
ANR-AR-DWG-005 | Door & Window Schedule | Architectural | Drawing | 0 | Rejected | 2026-08-29 | 2026-09-12 | 2026-09-09 | D - Rejected | 11 | TR-004
ANR-CV-DWG-016 | Site Grading Plan | Civil | Drawing | 1 | Rejected | 2026-09-21 | 2026-10-05 | 2026-10-06 | D - Rejected | 15 | TR-008
ANR-CV-DWG-017 | Storm Water Drainage | Civil | Drawing | 1 | Draft |  |  |  | -
ANR-CV-DWG-018 | External Road Layout | Civil | Drawing | 0 | Under Review | 2026-09-22 | 2026-10-06 |  | - | 23 | TR-008
ANR-HS-MS-019 | Site Safety Plan | HSE | Method Statement | 1 | Approved | 2026-09-08 | 2026-09-22 | 2026-09-22 | A - Approved | 14 | TR-005
ANR-HS-MS-020 | Lifting Plan - Tower Crane | HSE | Method Statement | 1 | Submitted | 2026-09-18 | 2026-10-02 |  | - | 27 | TR-008
ANR-ME-DWG-011 | Chilled Water Riser Diagram | MEP | Drawing | 1 | Approved | 2026-09-08 | 2026-09-22 | 2026-09-22 | A - Approved | 14 | TR-006
ANR-ME-DWG-012 | Electrical Single Line Diagram | MEP | Drawing | 2 | Approved with Comments | 2026-08-09 | 2026-08-23 | 2026-08-25 | B - Approved as Noted | 16 | TR-001
ANR-ME-DWG-013 | Fire Alarm Layout | MEP | Drawing | 0 | Under Review | 2026-08-26 | 2026-09-09 |  | - | 50 | TR-004
ANR-ME-DWG-014 | Plumbing Riser | MEP | Drawing | 0 | Approved | 2026-09-08 | 2026-09-22 | 2026-09-23 | A - Approved | 15 | TR-006
ANR-ME-DWG-015 | HVAC Duct Layout L1 | MEP | Drawing | 2 | Under Review | 2026-09-03 | 2026-09-17 |  | - | 42 | TR-005
ANR-QC-MS-021 | Concrete Pour Inspection Plan | QA/QC | Method Statement | 2 | Approved | 2026-08-10 | 2026-08-24 | 2026-08-22 | A - Approved | 12 | TR-001
ANR-QC-RPT-022 | Rebar Testing Report | QA/QC | Report | 1 | Submitted | 2026-08-12 | 2026-08-26 |  | - | 64 | TR-002
ANR-ST-DWG-006 | Foundation Layout | Structural | Drawing | 1 | Approved | 2026-09-07 | 2026-09-21 | 2026-09-13 | A - Approved | 6 | TR-005
ANR-ST-DWG-007 | Raft Reinforcement Details | Structural | Drawing | 0 | Approved | 2026-10-02 | 2026-10-16 | 2026-10-14 | A - Approved | 12 | TR-009
ANR-ST-DWG-008 | Column Schedule | Structural | Drawing | 2 | Approved | 2026-09-08 | 2026-09-22 | 2026-09-20 | A - Approved | 12 | TR-006
ANR-ST-DWG-009 | Slab Post-Tension Layout | Structural | Drawing | 0 | Approved | 2026-08-17 | 2026-08-31 | 2026-08-31 | A - Approved | 14 | TR-003
ANR-ST-DWG-010 | Shear Wall Details | Structural | Drawing | 1 | Approved with Comments | 2026-08-21 | 2026-09-04 | 2026-08-30 | B - Approved as Noted | 9 | TR-003
Red due date = overdue (no response by the 15-Oct-26 status date). Days Open counts to the status date until a response is returned.

## Transmittals
TRANSMITTAL LOG
Transmittal No. | Date | To | Purpose | No. of Docs | Status
TR-001 | 2026-08-05 | Client - Al Noor Developments | For Approval | 3 | Open
TR-002 | 2026-08-12 | Consultant - Gulf Design Partners | For Information | 1 | Open
TR-003 | 2026-08-17 | Client - Al Noor Developments | For Review | 2 | Closed
TR-004 | 2026-08-26 | Client - Al Noor Developments | For Information | 3 | Open
TR-005 | 2026-09-03 | Client - Al Noor Developments | For Information | 3 | Open
TR-006 | 2026-09-08 | Client - Al Noor Developments | For Approval | 3 | Closed
TR-007 | 2026-09-13 | Consultant - Gulf Design Partners | For Review | 1 | Closed
TR-008 | 2026-09-18 | Client - Al Noor Developments | For Information | 3 | Open
TR-009 | 2026-10-02 | Consultant - Gulf Design Partners | For Approval | 2 | Open
Formulas:
Date = MINIFS('Document Register'!$G5:G26,'Document Register'!$L5:L26,[Transmittal No.])

## Lists
Status | Discipline | Doc Type | Review Code
Draft | Architectural | Drawing | A - Approved
Submitted | Structural | Method Statement | B - Approved as Noted
Under Review | MEP | Material Submittal | C - Revise & Resubmit
Approved | Civil | Report | D - Rejected
Approved with Comments | HSE | Calculation | -
Rejected | QA/QC | Specification
Superseded