## Summary
SUBMITTAL SUMMARY
Concept project · fictional sample data · template by Mohammad Gulab
Status | Count | KPI | Value
Approved |  | First-time approval rate
Approved as noted |  | Avg. turnaround (days)
Revise & resubmit |  | Returned late
Rejected |  | Still under review
Under review
Total

## Submittal Register
MATERIAL SUBMITTAL REGISTER — Waterfront Residences (Concept)
Concept project · fictional sample data · template by Mohammad Gulab · Review period (days) in cell B4
Review period: | 14 | days |  | Data date: | 2026-10-25 |  | Codes: A Approved · B Approved as noted · C Revise & resubmit · D Rejected
Submittal No. | Rev | Spec Section | Material / Item | Supplier | Submitted On | Review Due | Returned On | Review Code | Status | Turnaround (days) | Late? | Remarks
SUB-03-001 | 0 | 03 30 00 | Ready-mix concrete C40/50 mix design | Supplier B | 2026-08-24 |  | 2026-09-02 | A
SUB-03-002 | 0 | 03 41 00 | Precast hollow-core slabs 200 mm | Supplier B | 2026-08-27 |  | 2026-09-03 | B
SUB-03-003 | 0 | 03 41 00 | Precast stair flights & landings | Supplier B | 2026-08-30 |  | 2026-09-07 | B
SUB-03-004 | 0 | 03 20 00 | Reinforcement steel B500B | Supplier B | 2026-09-02 |  | 2026-09-18 | A
SUB-07-005 | 0 | 07 13 00 | Bituminous waterproofing membrane | Supplier D | 2026-09-05 |  | 2026-09-11 | C
SUB-07-006 | 0 | 07 21 00 | Rigid insulation boards XPS 50 mm | Supplier B | 2026-09-08 |  | 2026-09-23 | B
SUB-08-007 | 0 | 08 11 13 | Steel fire-rated doors 60 min | Supplier C | 2026-09-11 |  | 2026-09-21 | A
SUB-08-008 | 1 | 08 51 13 | Aluminium windows, thermal break | Supplier B | 2026-09-14 |  | 2026-09-20 | D
SUB-09-009 | 0 | 09 30 13 | Porcelain floor tiles 600×600 | Supplier E | 2026-09-17 |  | 2026-09-29 | B
SUB-09-010 | 0 | 09 91 23 | Interior emulsion paint system | Supplier E | 2026-09-20 |  | 2026-10-01 | A
SUB-22-011 | 0 | 22 11 16 | PPR water supply pipes & fittings | Supplier C | 2026-09-23 |  | 2026-10-08 | B
SUB-23-012 | 0 | 23 31 13 | GI ductwork & accessories | Supplier E | 2026-09-26 |  | 2026-10-04 | A
SUB-26-013 | 0 | 26 05 19 | LV power cables & wires | Supplier A | 2026-09-29 |  | 2026-10-14 | C
SUB-26-014 | 0 | 26 24 16 | Distribution boards | Supplier E | 2026-10-02 |  | 2026-10-15 | B
SUB-21-015 | 0 | 21 13 13 | Fire sprinkler heads | Supplier D | 2026-10-05 |  | 2026-10-17 | A
SUB-32-016 | 0 | 32 12 16 | Asphalt wearing course | Supplier D | 2026-10-08
SUB-05-017 | 0 | 05 50 00 | Embedded steel plates & anchors | Supplier A | 2026-10-11 |  | 2026-10-23 | B
SUB-07-018 | 0 | 07 92 00 | Joint sealants, façade | Supplier D | 2026-10-14