## Dashboard
PROJECT DASHBOARD — Waterfront Residences (Concept)
Concept project · fictional sample data · template by Mohammad Gulab · all figures calculate from the Activities sheet
PLANNED |  | ACTUAL | VARIANCE | SPI (actual ÷ planned)
Status | Activities
Complete
On track
Minor delay
Delayed

## Activities
ACTIVITY PROGRESS — Waterfront Residences (Concept)
Concept project · fictional sample data · template by Mohammad Gulab · Data date in cell B4
Data date: | 2026-10-25
WBS | Activity | Area | Planned Start | Planned Finish | Weight % | Planned % | Actual % | Variance | Status
1.1 | Site mobilisation & enabling works | Site works | 2026-03-01 | 2026-03-31 | 3% |  | 100%
1.2 | Excavation & dewatering | Substructure | 2026-03-20 | 2026-05-10 | 6% |  | 100%
1.3 | Raft foundation & waterproofing | Substructure | 2026-05-01 | 2026-06-30 | 10% |  | 100%
2.1 | Precast columns & beams — Block A | Superstructure | 2026-06-15 | 2026-09-15 | 12% |  | 92%
2.2 | Hollow-core slabs — Block A | Superstructure | 2026-07-01 | 2026-10-15 | 10% |  | 85%
2.3 | Precast columns & beams — Block B | Superstructure | 2026-08-15 | 2026-11-30 | 12% |  | 48%
2.4 | Hollow-core slabs — Block B | Superstructure | 2026-09-01 | 2026-12-31 | 10% |  | 30%
3.1 | Blockwork & partitions | Finishes | 2026-09-15 | 2027-01-31 | 8% |  | 22%
3.2 | MEP first fix | MEP | 2026-09-01 | 2027-01-15 | 9% |  | 25%
3.3 | Façade & windows | Envelope | 2026-10-15 | 2027-03-15 | 8% |  | 4%
4.1 | Internal finishes | Finishes | 2026-12-01 | 2027-04-30 | 7% |  | 0%
4.2 | Testing, commissioning & handover | MEP | 2027-03-15 | 2027-05-31 | 5% |  | 0%
TOTAL / WEIGHTED

## S-Curve
S-CURVE — cumulative progress
Concept project · fictional sample data · template by Mohammad Gulab
Month | Planned cum. % | Actual cum. %
2026-03-28 | 3.6% | 2%
2026-04-28 | 7.6% | 5.5%
2026-05-28 | 13.5% | 11%
2026-06-28 | 20.4% | 19%
2026-07-28 | 27.2% | 27%
2026-08-28 | 35.6% | 35%
2026-09-28 | 49.1% | 42%
2026-10-28 | 61%
2026-11-28 | 72.5%
2026-12-28 | 81.8%
2027-01-28 | 88.1%
2027-02-28 | 91.4%
2027-03-28 | 94.3%
2027-04-28 | 97.8%
2027-05-28 | 99.8%