## Summary
RFI SUMMARY
Concept project · fictional sample data · template by Mohammad Gulab
KPI | Value | Discipline | Total | Open | Responded | Closed
Total RFIs |  | Structural
Open |  | Architectural
Responded |  | MEP
Closed |  | Civil
Overdue
Avg. response time (days)

## RFI Log
RFI LOG & TRACKER — Waterfront Residences (Concept)
Concept project · fictional sample data · template by Mohammad Gulab · Data date in cell B4
Data date: | 2026-10-25 |  | Status key: Open · Responded · Closed ¦ Overdue = open past its response due date
RFI No. | Date Raised | Discipline | Subject | Raised By | Addressed To | Priority | Response Due | Date Responded | Status | Days Open | Overdue? | Remarks
RFI-001 | 2026-08-31 | Structural | Clarify rebar lap length at transfer slab, Grid C/4 | Project Engineer | Structural Consultant | Medium | 2026-09-07 | 2026-09-02 | Closed
RFI-002 | 2026-09-01 | Architectural | Confirm façade panel joint width on east elevation | Site Engineer | Architect | Medium | 2026-09-08 | 2026-09-11 | Closed
RFI-003 | 2026-09-03 | MEP | Conflict between AC duct and beam B-12 at Level 3 | Project Engineer | MEP Consultant | Low | 2026-09-13 | 2026-09-08 | Closed
RFI-004 | 2026-09-06 | Structural | Precast hollow-core plank bearing detail at core wall | Project Engineer | Structural Consultant | High | 2026-09-11 | 2026-09-09 | Closed
RFI-005 | 2026-09-07 | Civil | Invert level mismatch, manhole MH-07 vs drawing | Project Engineer | Civil Consultant | Low | 2026-09-17 | 2026-09-12 | Closed
RFI-006 | 2026-09-09 | Architectural | Door schedule: fire rating for stair core doors | Project Engineer | Architect | Medium | 2026-09-16 | 2026-09-19 | Closed
RFI-007 | 2026-09-12 | MEP | Sleeve sizes for plumbing risers through PT slab | Doc Controller | MEP Consultant | Medium | 2026-09-19 | 2026-09-23 | Responded
RFI-008 | 2026-09-14 | Structural | Embed plate location for façade brackets, Level 5 | Site Engineer | Structural Consultant | High | 2026-09-19 | 2026-09-17 | Responded
RFI-009 | 2026-09-17 | Architectural | Finish for lobby feature wall — sample approval | MEP Engineer | Architect | Medium | 2026-09-24 | 2026-09-27 | Closed
RFI-010 | 2026-09-18 | Civil | Retaining wall weep-hole spacing | Doc Controller | Civil Consultant | Low | 2026-09-28 | 2026-09-23 | Closed
RFI-011 | 2026-09-19 | MEP | Electrical room ventilation rate | QA/QC Engineer | MEP Consultant | Medium | 2026-09-26 | 2026-09-26 | Responded
RFI-012 | 2026-09-22 | Structural | Column C-21 dimension differs between GA and section | MEP Engineer | Structural Consultant | High | 2026-09-27 | 2026-09-30 | Closed
RFI-013 | 2026-09-23 | Architectural | Balcony balustrade height at Type B units | Project Engineer | Architect | Low | 2026-10-03 | 2026-10-05 | Closed
RFI-014 | 2026-09-27 | MEP | Fire pump room drainage provision | QA/QC Engineer | MEP Consultant | Medium | 2026-10-04 | 2026-10-04 | Responded
RFI-015 | 2026-09-29 | Structural | Precast stair landing connection detail | QA/QC Engineer | Structural Consultant | Low | 2026-10-09 | 2026-10-02 | Closed
RFI-016 | 2026-10-01 | Civil | Asphalt build-up for internal roads | Project Engineer | Civil Consultant | High | 2026-10-06 | 2026-10-07 | Responded
RFI-017 | 2026-10-03 | Architectural | Ceiling height in corridor below services | MEP Engineer | Architect | Low | 2026-10-13 | 2026-10-11 | Responded
RFI-018 | 2026-10-03 | MEP | Location of main DB in Block 2 | QA/QC Engineer | MEP Consultant | Low | 2026-10-13 | 2026-10-14 | Closed
RFI-019 | 2026-10-05 | Structural | Grout specification for precast column sockets | Doc Controller | Structural Consultant | Medium | 2026-10-12 | 2026-10-09 | Responded
RFI-020 | 2026-10-08 | Architectural | Tile setting-out for wet areas | Doc Controller | Architect | Low | 2026-10-18 |  | Open
RFI-021 | 2026-10-10 | MEP | Kitchen exhaust riser route | Project Engineer | MEP Consultant | Low | 2026-10-20 | 2026-10-14 | Closed
RFI-022 | 2026-10-12 | Structural | Construction joint location in raft foundation | QA/QC Engineer | Structural Consultant | Low | 2026-10-22 |  | Open